Project Schedule
and Deliverables
Prof. Dr. Dirk Riehle
Friedrich-Alexander University Erlangen-Nürnberg
PROD-PROJ A02
[Speaker Notes: It is Friedrich-Alexander University Erlangen-Nürnberg – FAU, in short. Corporate identity wants us to say “Friedrich-Alexander University”.]

---
Course Schedule
#	Deliverables
01	Team contract
02	-
03	WP1: Market research
04	-
05	WP2: Buyer and user personas; Competitor analysis
06	-
07	WP3: Market potential; Market strategy
08	-
09	WP4: Growth projection; Pricing; Revenue structure
10	-
11	WP5: Cost structure; Product profitability; KPIs
12	-
13	WP6: Distribution strategy; Communication strategy; Product roadmap
14	WP7: Final version incl. management summary
15	Product pitch

---
Work Effort by Work Package
[1]	Please plan ahead for interviews
WP1
[1]
WP2
WP7
WP6
WP5
WP4
WP3
3
(hard)
2
(avg)
1
(easy)

---
Types of Deliverables
- Business plan
  - In draft versions
  - In final version (once)
  - As presentation in class

---
Time of Day for Deliverables
- Right before class
  - Submit this week’s deliverables
- Unless it is the first week of the course
  - Then, deliverables are due by Friday midnight that week

---
CW #01 Deliverables Due
- Team contract
  - See https://oss.cs.fau.de/teaching/course-resources/student-team-contract/
- Submit package as zip-file on StudOn
  - Include original files + PDF printouts
- Continue submitting like this

---
CW #02 Deliverables Due
None

---
CW #03 Deliverables Due
- Work package 1 (WP1), contains
  - Agile business plan draft with sections
    - Market research
    - Win / loss analysis
    - Buyer and user personas
    - Revised as necessary
  - EXIST business plan draft with sections
    - 2. Geschäftsidee
    - 3.1 Marktsituation
    - 3.2 Alleinstellungsmerkmal und Kundennutzen
    - Revised as necessary
  - Interview transcriptions / notes

---
CW #04 Deliverables Due
None

---
CW #05 Deliverables Due
- Work package 2 (WP2), contains
  - Agile business plan draft with sections
    - Buyer and user personas
    - Competitor analysis
    - Revised as necessary
  - EXIST business plan draft with sections
    - 2. Geschäftsidee
    - Revised as necessary
  - Additional interview transcriptions / notes (if any)

---
CW #06 Deliverables Due
None

---
CW #07 Deliverables Due
- Work package 3 (WP3), contains
  - Agile business plan draft with sections
    - Market potential
    - Market strategy
    - Revised as necessary
  - EXIST business plan draft with sections
    - 3.4 Markteintritt
    - Revised as necessary
  - Additional interview transcriptions / notes (if any)

---
CW #08 Deliverables Due
None

---
CW #09 Deliverables Due
- Work package 4 (WP4), contains
  - Agile business plan draft with sections
    - Growth projection
    - Pricing
    - Revenue structure
    - Revised as necessary
  - EXIST business plan draft with sections
    - 2.4 Projektplanung
    - 4.1 Finanzplanung
    - Revised as necessary
  - Additional interview transcriptions / notes (if any)

---
CW #10 Deliverables Due
None

---
CW #11 Deliverables Due
- Work package 5 (WP5), contains
  - Agile business plan draft with sections
    - Cost structure
    - Product profitability
    - KPIs
    - Revised as necessary
  - EXIST business plan draft with sections
    - 1. Executive summary
    - 2.1 Gründungsvorgeschichte
    - Revised as necessary
  - Additional interview transcriptions / notes (if any)

---
CW #12 Deliverables Due
None

---
CW #13 Deliverables Due
- Work package 6 (WP6), contains
  - Agile business plan draft with sections
    - Distribution strategy
    - Communication strategy
    - Product road-map
    - Revised as necessary
  - EXIST business plan draft with sections
    - 3. Markt / Wettbewerb
    - 4. Unternehmensplanung
    - 4.2 Unternehmensorganisation
    - Revised as necessary
  - Additional interview transcriptions / notes (if any)

---
CW #14 Deliverables Due
- Final complete business plan (WP7)
  - Includes management summary
  - Everything reviewed, formatted, cleaned-up
- Supplemental materials
  - Forms from the agile business plan
  - Spreadsheets with calculations
  - Interview transcriptions / notes

---
CW #15 Deliverables Due
- Final presentation (pitch to investors)
  - Matches the stage of the idea resp. startup (typically pre-seed)
    - Problem, Solution, Product
    - Market size and potential
    - Financial projections
    - Any backup slides you may need (after closing)
  - Max. duration of presentation is 15min + 5min Q&A

---
Thank you! Questions?
dirk.riehle@fau.de – http://oss.cs.fau.de
dirk@riehle.org – http://dirkriehle.com – @dirkriehle
DR

---
Credits and License
- Original version
  - © 2012-2019 Dirk Riehle, all rights reserved
- Contributions
  - ...